## Sheet1
Day of Sprint | Projected Progress | Actual Progress | Notes on Progress
Day 1 | 6 | 6
Day 2 | 6 | 5 | Adrienne was already working on the Dashboard Front End story before the sprint began, hence it was completed early.
Day 3 | 5 | 5
Day 4 | 5 | 4 | Adrienne completed the Files Front End story.
Day 5 | 4 | 3 | Nazmi completed the Contributors Front End story.
Day 6 | 4 | 3
Day 7 | 3 | 3
Day 8 | 3 | 2 | William completed the Issues Front End story.
Day 9 | 2 | 1 | Bryan completed the Timeline Front End story.
Day 10 | 2 | 1
Day 11 | 1 | 0 | Nazmi completed the top part of the Dashboard's Back End story as a proof of concept. All stories completed.
Day 12 | 1 | 0
Day 13 | 1 | 0
Day 14 | 0 | 0