## Sheet1
Day of Sprint | Projected Progress | Actual Progress | Notes on Progress
Day 1 | 6 | 6 | Bryan started learning how to query data with GraphQL and REST. Nazmi started working on his story.
Day 2 | 6 | 6
Day 3 | 6 | 6
Day 4 | 5 | 6
Day 5 | 5 | 5 | Bryan has completed the Timeline Back End story.
Day 6 | 4 | 4 | Nazmi has completed the Contributors Back End story.
Day 7 | 4 | 3 | Nazmi has completed the Users Front End story.
Day 8 | 3 | 1 | Nazmi has completed the Users Back End story. William has completed the Issues Back End story.
Day 9 | 3 | 1
Day 10 | 2 | 1
Day 11 | 2 | 0 | Adrienne has completed the Files Back End story. All stories have been merged to the master branch.
Day 12 | 1 | 0
Day 13 | 1 | 0
Day 14 | 0 | 0