## Sheet1
Day of Sprint | Projected Progress | Actual Progress | Notes on Progress
Day 1 | 4 | 4
Day 2 | 4 | 3 | Bryan has completed the Landing Page story and implemented dynamic querying functionality.
Day 3 | 4 | 3
Day 4 | 3 | 3
Day 5 | 3 | 3
Day 6 | 3 | 3
Day 7 | 2 | 3
Day 8 | 2 | 2 | Nazmi has completed the Dashboard Back End story and implemented dynamic querying functionality.
Day 9 | 2 | 2
Day 10 | 1 | 1 | William has completed the Issues Enhancement story and implemented dynamic querying functionality.
Day 11 | 1 | 0 | Adrienne has completed the Files Enhancement story and implemented dynamic querying functionality.
Day 12 | 1 | 0
Day 13 | 0 | 0
Day 14 | 0 | 0